3 - Construction Scope

  - general description

    - Scope

    - Codes, Standards and Documents

    - Drawings

    - Materials and Equipment

  - Job Description

    - General

    - Detailed Scope of Work

  - Construction requirement on the FMS's

  - Construction requirement on the BVS's

  - Construction requirement on the launchers / receivers

  - Construction requirement on the tie-in connection points

  - Construction requirement on the pipeline

  - construction equipment

  - Construction supervision.

  - discrepancy

3 - Construction Scope

  - General Description

    - Scope

This Scope of Work covers the minimum requirements for the construction of the ARAB GAS PIPE LINE PROJECT- PHASE II.

Contractor's construction scope of work shall include but not limited to  the supply of personnel, supervision, materials, consumable and construction equipment to construct and complete all the activities required for the completion of the PROJECT and provide it to the COMPANY ready and safe for operation as per these RFQ Specifications and Industry Codes and Standards.

The CONTRACTOR shall provide all personnel, supervision, co-ordination, tools and material as well as competent knowledge of construction for the Civil, Mechanical, Instrumentation, Electrical, Control and Telecommunication installation, and Cathodic protection, testing and putting into operation all the works as detailed in this RFQ tender book.

The CONTRACTOR shall execute all the works in a workmanlike manner so as to present a neat and finished appearance when completed.

The CONTRACTOR shall become familiar with the construction drawings of all disciplines and when laying out the work with regard to structural piping and mechanical features

The CONTRACTOR shall provide for approval a construction schedule, which will take into full consideration the availability or delivery of all equipment, materials and the target completion date required by the COMPANY.

The CONTRACTOR shall arrange his own inspection team and equipment for the quality control of the whole work. It shall be noted that although the COMPANY will appoint its own independent inspection agent.

No construction activity will be accepted unless it is accepted by CONTRACTOR inspection team and approved by the COMPANY inspection team according to the judged referenced code and standards within these RFQ specification but not limited to these stated in Exhibit- G

Construction shall include, but not be limited to:

- All functions associated with safe working at the Site.

- The preparation of foundations, road crossings, pipe trenches  and   reinstatement to original condition;

- The assembly, erection and installation of materials and equipment including all elements, components, interconnecting systems, access ways and platforms;

- Connection to the existing facilities including: piping, instrumentation, electrical and control systems, so as to avoid shutdown time required for the tie-ins; or to make this shut down time as minimum as possible.

- all isolating, unbolting, cleaning, de-gassing and safe evacuation of process media from existing facilities, upon depressurizing of the facilities by COMPANY and prior to commencement of tie-in work by CONTRACTOR.

- The performance of all inspections and testing;

- The provision of on-Site vendor representatives;

- The provision for COMPANY's use of on-Site office space and related furnishings, equipment and services; according to the COMPANY (PEA) on site services

- clean-up and removal of construction equipment and materials from the	construction /installation locations;

- CONTRACTOR shall include all functions associated with safe working at any site close to operating facilities, and comply with COMPANY's safety regulations.

- CONTRACTOR shall submit to the COMPANY, 6 weeks prior to any construction activities, a QA/QC plan to cover all construction, pre-commissioning and testing activities.

- The QA/QC will be used from the start of construction to the completion of the pre-commissioning activities and will be signed off by both CONTRACTOR and COMPANY .

- The QA/QC plan is subject to COMPANY approval.

- No construction activities will start until an agreed QA/QC plan is in place.

- The preparation of work procedures, submitted to COMPANY representative(s) at site for approval.  These procedures shall be submitted to COMPANY at least three weeks prior to start of the works.

- Provision of all necessary safety and construction equipment, such as gas detectors and scaffolding.

- Adhere to the contract changes procedures; report any changes/deviations from the design and contract specification formally to COMPANY for approval.

- Use a marker system for piping, pipelines and identification system for the equipment skids. The color code and identification systems shall be subject to COMPANY approval.

All work performed within COMPANY operating areas must be done under COMPANY’s Permit to Work (PTW) system.

This must be reflected in procedures submitted by CONTRACTOR and approved by COMPANY.

In case work is to be carried out in operating areas of third parties, the work is to be carried out under the third party Permit to work System.

Where appropriate and agreed by COMPANY, CONTRACTOR shall remove a part of the existing fence and fence the dedicated area for the to-be-installed facilities as shown on the relevant plot plan. The temporary fencing shall be 30 meters away from existing facilities. If these criteria cannot be met, the COMPANY Permit to Work System shall be adopted by CONTRACTOR.

CONTRACTOR shall take full account of lead times for safety discussions and processing of PTW in his implementation schedule.

Construction shall also include all related actions necessary to render the entire facility in a complete and proper state acceptable to COMPANY.

CONTRACTOR shall be responsible for obtaining all necessary permits to complete the work and shall pay all the fees for such permits.

    - Codes, Standards and Documents

construction scope includes but not limited to the piping, electrical, structural, concrete, control, telecommunication, instruments and equipment installation and shall conform to all applicable RFQ specifications and schedules and International Codes and Standards including but not limited to that provided in the “Exhibit-G, Data References and Contract’s General Specification”.

    - Drawings

CONTRACTOR shall provide all the Drawings and is responsible to show all details of the work by means of symbols/text the location of  foundations, structural steel. And skid(s) / package(s) piping etc according to the AFPC/ SCHEDUL-B requirements

    - Materials and Equipment

CONTRACTOR shall provide all materials, personnel, supervision tools and equipment for the construction and installation of the facilities in accordance with construction Drawings, and RFQ Specifications and Standards and Industry Codes and Standards.

CONTRACTOR shall identify critical items of equipment and other materials and shall make appropriate arrangements to order and have such items delivered to meet the required overall construction completion date.

  - Job Description

    - General

This job description for the construction activities covers the basic requirements for the supplying and installation of: FMS's, Gas Compressor units , Equipment, Civil, Mechanical, Piping, Instrumentation, Electrical, Control, Telecommunication, and Cathodic protection structural materials, and supplying and installation of the pipeline and the facilities in addition to the auxiliary and utilities system.

It is intended to supplement the construction drawings and to serve, as an installation guide for activities not detailed.

All works shall be done in accordance with all construction Drawings and all RFQ Specifications and Standards and Industry Codes and Standards, to be handed over to the COMPANY safe and operable PROJECT as per these RFQ contained in this tender and international codes, standards and specification.

    - Detailed Scope of Work

The Contractor's scope includes the supply of personnel, supervision, equipment, materials and consumable to perform the Civil, Mechanical, Instrumentation, Electrical, Control, Telecommunication, Pipeline  , Gas Compressor units , Fiscal Metering Station   ( FMS),  cathodic protection and tie-in connection points in addition to data transforming and connecting to the gas co-ordination center, with all construction work, completely constructed, installed, tested, dried  , safe operable and accepted by the COMPANY, in accordance with the RFQ Specifications and Standards and Industry Codes and Standards

The construction shall cover all the aspects included in the PROJECT which described but not limited to these stated in Exhibit (B) scope of work / section (1) general scope and definitions.

  - construction requirement at Al Foreqls Area

    - Construction and installation Fiscal Metering Station (FMS) at Al Foreqls area with 4 BCM/Y capacities.

The CONTRACTOR shall transport and install all equipment, skid unit(s)/package(s) to the designated sites and construct the required foundations, completely leveled and grouted and connect the skid/package piping to the Pipeline.

The Contractor's scope of work at Fiscal Metering Station (FMS) at Al Foreqls area includes but not limited to the following:

- Construct Site fencing as described in civil scope.

- construction of concrete foundation

- construction of pipe sleeper(s)/pipe support(s)

- Construct Piping System as indicated on CONTRACTOR supplied and approved drawings.

- Construct and install the three (3) of metering trains.

- Construct and install the cyclone separator.

- Construct the Fuel/Instrument gas skid with all related piping, instrument, electrical and buffer tank

- Construct and install Three gas compressor units.

- Install Control Panels and calibrate and interface all instruments

- Construct and install control and telecom System

- Install fire and gas detection system.

- Install diesel stand-by generator under sunshade

- Construct and install electrical system and to tie-in the electricity from the Over Head Power Line with the electric system in the FMS

- construct and install all electrical system like power, earthing, lighting, lightning and grounding

- construct all the required accessibilities and walk ways required for operation and maintenance requirements

- Construct and install blow down and flare system.

- construct buildings

- Construct and install portable water system and to tie-in and supply this water via 2” nozzle and 2” line with approximately length 500 meter from the station fence to 30 cubic meter tank with the proper elevation for the process and human water requirements.

- Any other activities such as, electrical, instrumentation etc

- Testing and documentation of completed systems

- Painting and insulation system

- As-Built Drawings

The FMS shall be constructed as minimum according to the typical drawing number 6000-10-07

    - Construction two launcher stations tagged L-6011&L-6015. see 3.5

- 3.4.2        Construction two receiver  stations tagged R -6018&R-6015 . see 3.5

  - construction requirement on the BVS,s

The CONTRACTOR’s scope includes but not limited to the supply, of personnel, supervision, materials, consumable and construction equipment to construct the Four (4) Block Valve Stations (BVS) tagged as follow:

BVS 6013

BVS 6014

BVS 6016

BVS 6017

With the required future, Telecommunication building and supply and install Line Break Detection/Control unit and deliver to the COMPANY as complete system.

The CONTRACTOR’s scope of work at the Block Valve Stations includes, but not limited to, the following:

- Site fencing as described in section 4 civil scope

- Install Piping and vent system considering the future requirements as described in section (5) mechanical scope.

- Construct all the required accessibilities.

- Install instruments

- Install cathodice protection

- Construct Block Valve Station and telecommunication building.

- Supply and install electric power system either using solar cells or installing overhead power line from the Syrian overhead power net if available as described in electrical scope.

- Testing and documentation of completed system

- Painting

- As-Built Drawings

  - construction requirement on the launcher / receiver stations

The CONTRACTOR’s scope includes the supply, of personnel, supervision, materials, consumable and construction equipment to

3.5.1 Construction and installing One (1) intermediate station (launching and receiving) tagged S-6015.

3.5.2 Construction and installing Receiver at the R-7003 in Aleppo PRMS tagged R6018.

3.5.3 Construction and installing Launcher at the Foreqls area tagged L-6011.

With the considering the future requirements connections stated in section (5) mechanical scope, Telecommunication building and supply and install Line Break Detection/Control unit and deliver to the COMPANY as complete system.

The CONTRACTOR’s scope of work at the pigging station sites includes but not limited to the following:

- Sites fencing

- Construction of concrete foundation for the receiver & launcher, lifting and inserting tools.

- Construction of concrete foundation for the anchor block

- Construction of concrete foundation for the vent stack and pipe supports

- Construct and install the launcher and/or receiver, lifting and inserting tools.

- Construct and install piping system considering the future requirements connection as described in section 5 mechanical scope.

- Construct instrumentation.

- Construction of pipe sleeper(s)/pipe support(s)

- Construction of all required accessibility (walk ways, platform, etc...)

- Construct Any other activities such as, electrical, instrumentation etc

- Testing, documentation of completed system

- Painting

- As-Built Drawings

  - Construction requirement on the tie-in connection points

The CONTRACTOR’s scope includes the supply, of personnel, supervision, materials, and consumable and construction equipment to construct the Four (4) tie-in connection points with existing gas net work facilities with the required Telecommunication, instrumentation, electrical insulation, isolation and deliver to the COMPANY as complete system.

These tie-in points will be constructed at the following locations:

    - Construction and installing tie-in with existing Future connection 36” flange. at BVS-6011 Al Foreqls area  of ARAB GAS PIPELINE PROJECT- PHASE I

    - Construction and installing tie-in with existing Future connection 36” flange. at R-7003 Near Aleppo Station of ARAB GAS PIPELINE PROJECT - PHASE II -PART I.

3.6.3    Construction and installing tie-in with 36" inlet/outlet of the gas compressor.

The Contractor's scope of work at the tie-in connection points

- Site fencing.

- CONSTRUCTION of concrete foundation

- Construct and install piping system.

- Construct instrumentation and telecommunication.

- CONSTRUCTION of pipe sleeper(s)/pipe support(s)

- CONSTRUCTION of all required accessibility (walk ways, platform, etc...)

- Any other activities such as, electrical, instrumentation etc

- Testing, documentation of completed system

- Painting

- As-Built Drawings

  - Construction requirement on the pipeline

The Contractor's scope includes the supply, of personnel, supervision, materials, and consumable and construction equipment to:

    - Construct one hundred eighty-six kilometer (186 km) of 36 inch API 5L X70 pipeline for PROJECT.

With the required Telecommunication, instrumentation, electrical insulation, class breaking, anchor and deliver to the COMPANY as complete system.

The pipe line construction activities include but not limited to the following:

- Soil investigations.

- The right of way clearing and grading.

- The trenches excavation and preparation.

- Area classification and line pipe stringing.

- All crossing with (roads, railway, swamps, wadis, rivers, power and telecom cables, power cables, irrigation channels, potable water system , sewerages and other pipelines etc….)

- Pipe line bending, welding, NDE, coating, lowering, fiber optic cable laying and backfilling.

- Cathodic protection system installation.

- Telecommunication and control system installation.

- Pipeline cleaning, sizing, hydro testing, drying and purging.

- Right of way cleaning up and marking

- Demobilization.

- As built drawings

  - Construction Equipments

CONTRACTOR shall supply all the construction personnel, supervision, equipment materials required for the proper installation and operation of all Civil, Mechanical, Pipeline, Cathodic protection, Instrumentation, Electrical, Control, Telecommunication and shall supply all materials for the complete system of the PROJECT.

  - construction Supervision

CONTRACTOR shall submit the construction organization chart indicating the chain of responsibility and the resume of the individual identified in the organization chart.

COMPANY has the power to reject any individual in the organization that does not have the training and or experience to do the job or affect the COMPANY prestige or Syrian Arab republic laws.

CONTRACTOR shall have experienced construction Supervision and be completely responsible of all activities such as:

    - All functions associated with safe working at the job sites and compliance with COMPANY's safety regulation.

    - Site surveys, site preparation, grading, roads, trenches, crossings, fencing, restoration to original conditions, etc.

    - Pick-up at port, loading, transportation, off-loading, unpacking, assembly, erection and installation of all supplied materials and equipment, elements, components, interconnecting systems, access ways, platforms etc

    - The preparation, make-up, installation, connection and testing of all interconnect components of the pipeline system etc.

    - The fabrication / installation of all piping, cable trays and supports.

    - The performance of all inspection and testing activities.

    - Supervision of on-site Vendor’s representative(s).

    - Turnover of complete pipeline and facility(s), to the COMPANY as per RFQ requirement and specifications within safe operation requirements.

    - And all other task stated in general scope in EXHIBIT B(scope of work)

  - discrepancies

In case a discrepancy arises or exists between codes, standards, drawings and documents, the most severe shall govern in the following priority:

3.10.1  RFQ tender book documents

3.10.2  (AFPC)  scopes and specifications

3.10.3  International industry codes and standards