EXHIBIT-C, “INVOICING AND PAYMENTS”

1.	CONTRACT PRICE FOR

1.1	With reference to the TYBICAL CONTRACT, it is mutually agreed between COMPANY and CONTRACTOR that for the complete performance of the work, COMPANY 	shall pay to CONTRACTOR the Lump Sum CONTRACT PRICE of:

- an amount /  1000000000 / S.P only one billion   Syrian Pounds

- an amount of / ________ / . Foreign Currency Portion

  - The Lump Sum CONTRACT PRICE comprises the sum of Lump Sum Contractor’s

shown in the Pricing Sheets.

1.3	The Pricing Sheets show the breakdown of the Lump sum CONTRACT PRICE per Activity. An Activity is in this context defined as a specific execution function for a Plant system or item indicated on the Pricing Sheets.

1.4	The price amounts shown for each Activity are deemed to be the full amount payable to CONTRACTOR for the complete performance of all WORK associated with that Activity, including, but not limited to, a proportional share in all other costs incurred by CONTRACTOR for WORK required under CONTRACT for which no specific Activity is defined.

1.5	The CONTRACT PRICE shall be paid by COMPANY as follows:

- COMPANY will pay an amount /  1000000000      / S.P only one billion   Syrian Pounds to The CONTRACTOR against services works inside Syrian Arab Republic territory.

- Foreign Currency Portion is to be paid by Foreign Currency transferable.

Signature :  _____________________   Date :  ________________

2.	PROGRESS PAYMENTS

For the calculation of the Value of Work Done ( VOWD ) at the end of each calendar month, a percentage complete shall be mutually agreed between COMPANY and CONTRACTOR for each Activity in accordance with the following guidelines:

| 2.1 Engineering |  |  |  |  |  | 5% |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  | Status |  |  |  |  |  |  |  | Percentage Payment |  |  |  |  |
| Engineering |  |  | - Basic Design approved. |  |  |  |  |  |  |  | 15% |  |  |  |  |
|  |  |  | - Detail Design approved. |  |  |  |  |  |  |  | 40% |  |  |  |  |
|  |  |  | - Manuals received and accepted |  |  |  |  |  |  |  | 20% |  |  |  |  |
|  |  |  | - As Built drawings received and accepted |  |  |  |  |  |  |  | 20% |  |  |  |  |
| Training |  |  | - Training of SGC’ staff |  |  |  |  |  |  |  | 5% |  |  |  |  |
| 2.2 Procurement and Transportation of Materials and Equipment to the job site 80% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  |  | Status |  |  |  |  |  |  | Percentage Payment |  |  |  |  |  |
| Equipment received at job site |  |  | - Compression Station Received - FMS Received - BVSs Received - Pigging Facilities Received - DCS System Received - Telecommunication System Received - Two Years Recommended Spare Parts Received - Spare Parts and materials Required by Company received - 36” pipeline received - Others |  |  |  |  |  |  | 22% 7 % 2% 2% 4% 3% 1% 1% 57% 1% |  |  |  |  |  |
| 2.3 Construction Activities 15% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1 Mobilization & Supervision at job site |  |  |  |  |  |  | 5% |  |  |  |  |  |  |  |  |
| 2.3.1.A Mobilization 2.3.1.B demobilization |  |  |  |  |  |  | 3% 1% |  |  |  |  |  |  |  |  |
| 2.3.1.C Supervision at job site ## Project Manager ## Civil ## Pipeline Welding Mechanical Instrumentation/Control & Telecomm. Electrical |  |  |  |  |  |  | 1111% 1% |  |  |  |  |  |  |  |  |
| 2.3.2 Construction and Pre commissioning of Facilities 95% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2A Survey 1.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2B Fiscal Metering Stations 7% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  | Status |  |  |  |  |  | Percentage Payment |  |  |  |  |  |  |  |
|  |  | - Civil 40% - site preparation to final grade - concrete pours complete - structural steel complete - buildings complete - fencing - final site preparation and clean-up complete |  |  |  |  |  | 20% 15% 15% 30% 5% 15% |  |  |  |  |  |  |  |
|  |  | - Mechanical 35% - skid/equipment installation - piping complete - instrument hook up - paint and insulation - cleaning, drying and Hydro test |  |  |  |  |  | 40% 25% 15% 10% 10% |  |  |  |  |  |  |  |
|  |  | - Electrical 10% - Equipment installed - cable laid & terminated - MCC wired - grounding/lighting complete - System Tested |  |  |  |  |  | 30% 20% 20% 15% 15% |  |  |  |  |  |  |  |
|  |  | - Control/Telecommunication 15% -Hardware installed Control Telecom. -System Configured Control Telecom -Interfacing to GCC System SCADA Telecom |  |  |  |  |  | 30% 15% 30% 10% 10% 5% |  |  |  |  |  |  |  |
| 2.3.2C Block Valve Stations |  |  |  |  |  |  |  | 13% |  |  |  |  |  |  |  |
| Description |  |  |  | Status |  |  |  | Percentage Payment |  |  |  |  |  |  |  |
| BVS, SDV & Pigging area |  |  |  | - Civil 40% - site preparation to final grade - concrete pours complete - structural steel complete - buildings complete - paving -fencing and final site preparation and clean-up complete - Mechanical 35% - equipment installed - piping/valves complete - instrument hook up - paint and insulation - testing complete - Electrical 10% - Equipment installed - cable laid & terminated - grounding/lighting complete - System Tested |  |  |  | 10% 15% 15% 40% 5% 15% 15% 55% 10% 10% 10% 35% 30% 20% 15% 40% 20% 30% 10% |  |  |  |  |  |  |  |
|  |  |  |  | - Control/Telecommunication 15% - Hardware installed Control Telecom. - System Configured Control Telecom |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2.D Pipeline Construction 68% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - R.O.W &Excavation - Welding - X-ray -Lowering and back filling Cleaning - Hydro test - Drying - Sign board installed - R.O.W. cleaned |  |  |  | 15% 30% 5% 15% 5% 10% 5% 5% 10% |  |  |  |  |  |  |  |
| 2.3.2.E Cathodic Protection 2% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | -deep wells drilled & crossing installed -testing stations installed -current monitoring stations installed -rectifiers installed -transformers installed -lightening and surge protection installed -anodes installed -panels installed -cables installed and connected -system tested |  |  |  | 20% 10% 15% 5% 5% 10% 5% 5% 15% 10% |  |  |  |  |  |  |  |
| 2.3.2.F Commissioning (including initial spare parts and consumable) & Start-up 3.5% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - FMS commissioned, Successful start-up and introducing of Hydrocarbon. -Gas compression Station commissioned successfully - BVSs commissioned successfully - Pipeline commissioned |  |  |  |  |  |  |  |  |  |  | 20% 45% 5% 30% |  |  |  |

Bidder should specify  the price to be paid for each item.

Signature:  _______________________  Date:  _______________________