PEA - APPENDIX  7

SCHEDULE OF Contractor's SUBMITTALS

Submittal Item 			Initial Submittal 	Frequency

- Safety Policy 			* 	n/a

- Safety statistics			With monthly report 	monthly

monthly return

- Incident reports 	 		Within 24 hours 	n/a

- Certification of lifting 	 		Before start of work 	n/a

gear

- Intended SPIRs form 			*	n/a

- Completed SPIR form 	 		* 	n/a

- List of special tools 	 		* 	n/a

testing equipment

- Full inventory of 	 		30 days prior to start-up 	n/a

operating supplies

- Notice of Force Majeure 	 		Within 72 hours 	n/a

- Notice of Changes 	 		Within 72 hours 	n/a

- Approved Monthly 	 		5 days after the end 	monthly

Schedule 			of the month

- Invoice 	 		After approval of Payment 	monthly

Schedule

- Final Invoice 	 		On issue of Certificate 	n/a

of Provisional Acceptance

- Contractor’s Vendor List  	 		Before signing the contract    	n/a

- Insurance certificates 	 		* 	n/a

- Errors in Company’s 	 		Prior to start work 	as required

drawings

- Contract Implementation 			*

- Site Const. Schedule	 		* 	as changes

occur

- Construction Equipment 	 		- idem - 	- idem -

Schedule

Submittal Item 			Initial Submittal 	Frequency

-Testing schedules 	 		* 	- idem -

- Commissioning schedule 	 		60 days prior to commissioning - idem -

-Tie-In schedule 	 		* 	- idem -

- Notice of shut down(s) 	 		15 days before shut downs 	- idem -

- Completion and Turnover	 		Near completion 	n/a

Schedule

- Notice that facility is:

* ready for introduction 	 		7 days before completion  	n/a

of process media 			of precommissioning

* ready for Acceptance 	 		7 days before completion of 	n/a

Testing 			commissioning

- Notice for end Warranty 	 		30 days before end of Warranty	n/a

- Weekly site report 	 		2 days before site meeting	 - idem -

- Minutes of weekly mtg.	 		2 days after meeting 	weekly

- Monthly progress report 	 		5 days after the end of the 	monthly

month

- List of and Schedule for 	 		* 	n/a

submittal of information

- Register showing status  	 		With monthly progress report 	monthly

of information submittals

- Procedure for submittal 	 		* 	n/a

and Review of drawings

- Drawings 	 		Promptly on completion 	n/a

- Drawing Status List 	 		With Monthly Progress Report monthly

- Procedures for work 	 		30 days prior to construction 	n/a

within operating areas

- Samples 	 		30 days prior to 	n/a

incorporation into the work

Submittal Item 			Initial Submittal 	Frequency

- Calculation books 	 		* 	n/a

- Manufacturer’s data 			* 	n/a

books

- Draft Pre-commissioning	 		60 days prior to start of 	n/a

Manual 			pre-commissioning

- Final Pre-commissioning	 		30 days prior to start of 	n/a

Manual 			pre-commissioning

- Draft Permit to Work 	 		* 	n/a

System

- Final Permit to Work 	 		* 	n/a

System

- Completed test/check 	 		prior to issue of certificate 	n/a

sheets			of provisional acceptance

- Draft Start-up Manual	 		60 days prior to start-up 	n/a

- Final Start-up Manual 	 		30 days prior to start-up 	n/a

- Draft Acceptance Test 	 		60 days prior to start-up 	n/a

Manual

- Final Acceptance Test 	 		30 days prior to start-up 	n/a

Manual

- "As-built" drawings 	 		at the introduction 	n/a

of process media

- Operation and Maint.	 		30 days prior to planned 	n/a

Manuals 			start- up

- H.S.E. Manual 	 		Prior to Commissioning

- Organisation Chart 	 		*	 n/a

- Quality Control Program 	 		* 	n/a

*	To be provided by Contractor